## Cover
TEST PLAN
Project Name | Website Tiki |  |  | Reviewer | Đỗ Chí Thành / Lê Đặng Xuân Bách
Project Code | WebTiki |  |  | Review date | 2024-10-31
Creator | Đỗ Chí Thành |  |  | Approver | Đỗ Chí Thành
Version | v1.0 |  |  | Approval Date | 2024-11-01
Record of change
Effective Date | Version | Change Item | A, D, M | Change description
2024-10-26 | v1.0 | Initial
Index
Sheet Name | Description |  |  |  | Note
Cover | Title page
Test Policy | - General policy for Test process, Test case design, Test Data - List of requirements to Test/not Test - Exit criteria for testing - Suspension criteria and Resumption requirements
Test Management | - Test scope - Deliverable - Management method - Risk - Assumption - Training plan
Test Strategy | Identification of Test level, Test types, Test environments, Test data and Enviroment for test
Master Schedule | Introduction and Define team, master schedule for testing
Appendix | - Description and detailed definition of Test level, types and techniques - List of Terminologies and definition/explanation |  |  |  | For Reference only
Reference Document
Name |  |  |  | Version | Note
WebTiki_ScreenDesign_v0.5 |  |  |  | 0.5
Note on E10: ====== ID#AAAAHNbKGmo (2020-11-08 05:44:12) - A: Added - D: Deleted - M: Modified

## Test Policy
Test Policy
Test process policy
Description of policies of testing process.
| # | Description | Responsibility | Note
| 1 | Testing Objectives | Team | Ensure that the testing process is carried out in a systematic, accurate, and efficient manner. Ensure that all testing requirements and standards have been complied with. Confirm the features, performance, and reliability of the software.
| 2 | Testing Process | Leader | Define the test scope based on requirements and standards. Develop a testing plan, including testing schedules, resources, and methods. Prepare a test environment, including hardware, software, and sample data. Carry out testing activities according to the approved plan. Record test results and report bug detections.
| 3 | Testing Environment | Leader | The testing environment must be established and maintained in accordance with the defined requirements and standards. The test environment must be consistent with the actual environment in which the software will operate, including hardware, software, and data. Appropriate software versions and databases should be provided to perform tests and ensure the accuracy of the software.
| 4 | Division of responsibilities | Leader | The project manager is responsible for determining the scope, plan and progress of the test. The testing team is responsible for carrying out testing activities and reporting on test results. The software development team is responsible for providing a testing environment and support to the testing team.
| 5 | Error management | Leader & Member | Identify, record, and track errors detected during testing. Prioritize and resolve detected errors according to an established error management process. Double-check the faults that have been corrected to ensure the effectiveness of the testing process.
| 6 | Evaluation and improvement | Leader & Member | Evaluate the performance, quality, and effectiveness of the testing process. Gather feedback and suggestions for improvements to enhance testing in the future.
| 7 | Updates and Re-Evaluations | Leader & Member | Check and update the testing policy periodically to ensure it reflecting changes in the development environment and the requirements of project.
Test case design policy
Description of policies of test case design.
| # | Items | Note
| 1 | Purchase history | Check the display of order details. Confirm the correct order status update. Test automation for order status viewing.
| 2 | Product Filter | Performance testing with large quantities of products. Check the accuracy of the filtering results. Test automation for product filtering.
| 3 | Product Search | Check the accuracy of your search results. Test automation for product discovery.
| 4 | Product details | The test displays product details. Test automation for product detailing.
| 5 | Cart | Check add, remove, and update products in the cart. Check the checkout feature and cart view function. Automate cart-related testcases.
Quality metric
Description of target
| # | Items | Target | Note
| 1 | Purchase history |  | Ensure full testing of scenarios, displaying various order details, products, and statuses.
| 2 | Product Filter |  | Ensure the quality and accuracy of product filtering.
| 3 | Product Search |  | Ensure the quality and accuracy of search.
| 4 | Product details |  | Make sure to display the detailed information of the product
| 5 | Cart |  | The error detection rate should be kept < 5%.
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
| # | Criteria | Priority | Note
| 1 | 80% of completed test cases / total test cases (test coverage > 80%) | High | Carry out test cases with highest priority first, then increase gradually.
| 2 | Test successful coverage >= 80% | Normal
| 3 | Software is correct with SRS | High
Suspension Criteria and Resumption Requirements
Specify when to pause in a series of tests and requirements for resumption of test activities.
| # | Suspension Criteria | Note
| 1 | When a defect is introduced that cannot allow any further testing
| 2 | A specific holiday shuts down both development and testing (Tet Holiday)
| 3 | If there is any network, hardware problem in the organisation, we can suspend testing
| 4 | If we got more pending requests with the development team
| # | Resumption Requirements | Note
| 1 | When the particular issue has been addressed and solved

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test plan |  |  | Leader / Testers
2 | Create test design |  |  | Tester
3 | Create test cases |  |  | Tester
4 | Create test data |  |  | Teseter
5 | Execute system test |  |  | Teseter
6 | Defects list |  |  | Teseter
7 | Create test report |  |  | Leader / Testers
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2024-10-29 | Test leader | Test manager, Team | This document itself
2 | Test cases | 2024-10-29 | Test leader | Test manager, Team
3 | Defect logs | 2024-10-29 | Test leader | Test manager, Team
4 | Test report | 2024-10-29 | Test leader | Test manager, Team
Management method
Describe the management method of test process.
# | Object | Method |  |  | Note
1
2
3
Risks
Listing of all risks of test process and action to mitigate the risk and do if risk become reality.
# | Condition |  | Mitigation |  | Contingency
1 | Team members lack experience in software testing domain |  | Plan training course to skill up your members |  | 1. Connect with a training organization 2. Attend mandatory training 3. Quality test
2 | The development team improved the code which led to the testing process being paused |  | Accept this risk |  | Contact the development team
3 | The project schedule is too tight; it's hard to complete this project on time |  | Set test priority for each test case and execute the test case with the highest priority |  | 1. Determine the priority for each test case 2. Set priority for each test case 3. Follow the priority level
4 | Members misunderstood the request |  | Organize to review and analyze requirements to member before starting the testing process |  | 1. Hold a meeting 2. Review required 3. Inspections
5 | Employees reduce working performance after Tet holiday |  | Accept this risk |  | OT to keep up with the schedule
Assumption
Listing of all assumption of test process.
# | Type | Description
1
2
Training Plan
Plan training for test team.
# | Training Topic | Description |  | Responsibility | Start Date | End Date
1
2
3
Note on E32: ====== ID#AAAAHNbKGmc (2020-11-08 05:44:12) steps keep a risk from occurring or driving its impact to an acceptance level
Note on G32: ====== ID#AAAAHNbKGmk (2020-11-08 05:44:12) steps would have to be done if the risk were to become reality
Note on B41: ====== ID#AAAAHNbKGmY It can be (2020-11-08 05:44:12) - Requirement - Test Products - Test environment - Test tools ...

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | Unit testing | Integration Testing | System Testing | User acceptance testing
Test techniques
White box testing | x |  | x
Black box testing |  | x | x | x
Responsibility | Developer | Tester | Tester | Tester
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  |  | Note
All Functions of the ProlTM system described in screen design document, the functions are tested in order of priority from high to low (highest priority tested first) |  | WebTiki_ScreenDesign_V0.5
Test environment
Listing of environments use in test process.
Type | Environment |  |  |  | Note
Hardware | Laptop, Tablet, Smartphone |  |  |  | Standard Fsoft
OS | Window 10 64bit Mac10.14.5 Android 6.0 or higher
Software | Chrome version 130.0.6723.70 Firefox 70.0 Edge 44.18362.329.0
Database | MS SQL
Browser | IE/FireFox, Chrome
Network configured | LAN Wifi
Note on G10: ====== ID#AAAAHNbKGmg (2020-11-08 05:44:12) - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
STT | Worker / Doer | Position | Responsibilities
1 | Đỗ Chí Thành | Leader | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Xem lịch sử mua hàng
2 | Lê Đặng Xuân Bách | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Lọc sản phẩm
3 | Phan Trường Thịnh | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Tìm kiếm sản phẩm
4 | Đào Lưu Trọng Luân | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Xem chi tiết sản phẩm
5 | Lê Phi Vũ | Member | Read and Analyze Doccument, test design, test case, thực thi các test case, logs bug cho chức năng Giỏ hàng
Master Schedule
STT | Item | Start Date | End Date
1 | Create test plan | 2024-10-26 | 2024-11-01
2 | Create test design | 2024-10-26 | 2024-11-01
3 | Create test case
4 | Execute test and log bugs
5 | Evaluting exit criteria & Test report
6 | Review
| Task | Start day from 26/10/2024 | Duration
| Create test plan | 0 | 6
| Create test design | -1 | 6
| Create test case | -45593 | 0
| Execute test and log bugs | -45594 | 0
| Evaluting exit criteria & Test report | -45595 | 0
| Review | -45596 | 1
Detail Schedule
Liên kết

## Detail Schedule
# | Item | Responsibilities | October | [5 empty] | November
|  |  | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Create test plan | Team | bar: October 26 to November 1
2 | Create test design | Team | bar: October 26 to November 1
2.1 | Xem Lịch sử mua hàng | Đỗ Chí Thành
2.2 | Lọc sản phẩm | Lê Đặng Xuân Bách
2.3 | Tìm kiếm sản phẩm | Phan Trường Thịnh
2.4 | Xem chi tiết sản phẩm | Đào Lưu Trọng Luân
2.5 | Giỏ hàng | Lê Phi Vũ
2.6 | Review | Team
3 | Create test case
3.1 | Xem Lịch sử mua hàng | Đỗ Chí Thành
3.2 | Lọc sản phẩm | Lê Đặng Xuân Bách
3.3 | Tìm kiếm sản phẩm | Phan Trường Thịnh
3.4 | Xem chi tiết sản phẩm | Đào Lưu Trọng Luân
3.5 | Giỏ hàng | Lê Phi Vũ
3.6 | Review | Team
4 | Execute test and logs bug
4.1 | Xem Lịch sử mua hàng | Đỗ Chí Thành
4.2 | Lọc sản phẩm | Lê Đặng Xuân Bách
4.3 | Tìm kiếm sản phẩm | Phan Trường Thịnh
4.4 | Xem chi tiết sản phẩm | Đào Lưu Trọng Luân
4.5 | Giỏ hàng | Lê Phi Vũ
4.6 | Review | Team
5 | Evaluting exit criteria & Test report | Team
6 | Review | Team

## Appendix
Appendix
Term definition
# | Term | Definition/explanation
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
17
Glossary
#
1
1
2
3
4
#
4
5
6
7
8
9
10
11
12
13
14
Members
1 | 20130118 | Đỗ Chí Thành
2 | 20130199 | Lê Đặng Xuân Bách
3 | 20130181 | Phan Trường Thịnh
4 | 20130068 | Đào Lưu Trọng Luân
5 | 20130468 | Lê Phi Vũ
ss